## 1. Better Living & Recreation
SI 1.1 | Urban and land use planning to preserve historic settlements | Municipality | Responsible Party | Estimated Budget $ | Tentative Timeline
1.1.1 | Finalize the Urban and Land Use Plans for the Mulakhi and Ushguli communities. The urban planning documentation for Ushguli has already been completed three years ago and has been submitted to UNESCO. | Mestia | LSG & MoRDI/MoESD | No cost | 1 year
1.1.2 | Prepare and obtain approval for Urban and Land Use planning that covers the entire administrative territory of Mestia and Lentekhi Municipalities. | Mestia Lentekhi | Municipal Council | No cost | 3 years
1.1.3 | Create a basic master plan and inventory for architectural and historical monuments as part of the Urban Planning Documents. | Mestia Lentekhi | LSG & MoESD&MoC | No cost | 3 years
Results | Prevention of disorganized intrusion into the historical cultural fabric. Preservation of urban heritage. Compliance with architectural and urban requirements.
SI 1.2 | Tourism infrastructure development in accordance with the urban plans and development invesment | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
1.2.1 | Coordinate the intentions of stakeholders and developers, while adhering to rules and regulations that reflect tourism development priorities. | Mestia Lentekhi | DMO / Council/Mayor's office | No cost | Ongoing
1.2.2 | Mestia township center Seti: Complete the construction of the buildings and convert them into visitor service facilities, allocating space for the DMO visitors' center | Mestia | Municipality and GoG | TBD | 3 years
1.2.3 | Feasibility study for the new year-round ski area: Mestia-Qoluldi Lakes-Chaladi glacier, covering a distance of up to 8.6 km. | Mestia | MTA/MoESD | 500,000 EUR | 1 year
| Construction of the ropeway (gondola) Mulakji-Tetnuldi, distance of 3 km | Mestia | MTA/MoESD | 9 million UER | 2 years
| Design and construct a recreation area/spa, and fun park in close pDesign and construct a recreation area, spa, and fun park near the airport | Mestia | Municipality/MDF | TBD | 3 years
| Feasibility study for Lentekhi - Mt. Chutkharo ski/mountain resort (development plan for a large 4-season resort) | Lentekhi | MTA/MoESD | TBD / In progress | 1 year
1.2.4 | Rehabilitate and adapt the existing historic-ethnographic museum for visitors interpretation center | Lentekhi | Mayor/LSG/Donor | 100,000 EUR | 2 years
1.2.5 | Prepare a feasibility study for the Zeskho alpine camp, design the Ailama alpine camp, and undertake the reconstruction of the historical village of Makashi. | Lentekhi | MDF/RDA-MoESD | RDA contracted E&Y/CDA | Ongoing
1.2.6 | Plan for thye development of new summer adventure tourism products and businesses such as ziplines, rafting and kayaking, camping, etc. | Lentekhi | DMO/LSG | TBD | 5 years
1.2.7 | Conduct study for new oportunities for winter heliski and heli/ski-touring | Lentekhi | DMO/LSG | TBD | 3 years
Results | New products for winter and summer activities. Tourism development priorities reflected in the annual plan/budgets of the respected national agencies/ministries/companies.
SI 1.3 | Sustainable and quality energy supply | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
1.3.1 | Adopt an energy supply system tailored to the specific needs of tourism and residents, considering factors such as consumption patterns, residents and commercial users tariffs, and evaluating various technical and economic solutions. | Mestia | regulatory committee, MoESD, LSG | no cots | 5 years
1.3.2 | Conduct a feasibility study to increase the share of renewable energy, focusing on contributions and efficiency of small and medium-sized hydroelectric power plants (HHP) | Mestia Lentekhi | Private investment | TBD | 5 years
1.3.3 | Increase energy efficiancy for municipal buildings, domestic needs and private businesses | Mestia Lentekhi | Private investment | TBD | 5 years
1.3.4 | Conduct a feasibility study, environmental and economic impact assessment for the construction of a natural gas supply infrastructure. | Both | GOG | TBD | 5 years
Results | Stable and reliable energy supply for the region, while also taking into consideration environmentaEnsure a stable and reliable energy supply for the region, while also taking into consideration environmental and socio-economic needs.
SI 1.4 | Roads and regional connectivity | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
1.4.1 | Rehabilitation of state road Zugdidi - Jvari - Mestia - Lasdili with ongoing maintanance works. | Mestia, Letekhi | SRD/MoESD | TBD | Ongoing
| Reconstruction of Ushguli - Zagaro pass-Tsana road. | Mestia | SRD/MoESD | TBD | Ongoing
1.4.2 | Lentekhi interstate roads 102 km, 58 km paved form Lentekhi to Tsana, rehabilitation portion 44 km | Lentekhi | SRD/MoESD | TBD | Ongoing
1.4.3 | Lentekhi central road to villages paved total 28 km | Lentekhi | SRD/LSG | TBD | Ongoing
Results | Secure the Kutaisi-Zugdidi circular road, passing through Upper and Lower Svaneti, to expand the tourist area and provide additional self-drive tourism opportunitiessecure the Kutaisi-Zugdidi circular road, passing through Upper and Lower Svaneti, to expand the tourist area and provide additional self-drive tourism opportunities.
SI 1.5 | Public transportation | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
1.5.1 | Enhance public transport utilization and establish car-free zones in both the town and resort areas. | Mestia | LSG & Private | 100,000 EUR | 3 years
1.5.2 | Arrange a circular and internal public transport Mestia-Langer for locals and tourists. | Mestia | LSG & Private | 100,000 EUR | 1 year
1.5.3 | Establish a bus station (public-private) in Mestia for tourist destinations | Mestia | LSG / DMO | 50,000 EUR | 1 year
Results | Redistribution of tourist flows throughout the territory of Upper and Lower Svaneti. Improvement of residents' mobility.
SI 1.6 | National and international access | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
1.6.1 | Provision of Mestia Airport with modern navigation systems; Increae the number of flights to minimum 2 flights per day. | Mestia | Civil Aviation Agency/MoESD | tbd | 5 years
1.6.2 | Conduct feasibility study for the construction of a new airport in Chikhareshi/Lentekhi to assess technical and economic rationality. | Lentekhi | Civil Aviation Agency/MoESD | tbd | 3 years
Results | Increasing the frequency of regular flights and flight safety. Establishment of a new regional tourist hub.
SI 1.7 | Water supply & wastewater | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
1.7.1 | Upgrade water supply and treatment system for Mestia municipality in 15 communities along the central road. | Mestia | GOG | TBD | TBD
1.7.2 | Rehabilitation of WS and WWS systems for big communities along the main road for community centers (Mestia 16 Lentekhi 6) | Both | LSG | 2.5 million EUR | 5 years
Results | Significant improvement of communal services and minimization of environmental impact.
SI 1.8 | Solid waste management | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
1.8.1 | Set up a small waste transfer station in Mestia municipality near the village of Lakhani. | Mestia | GOG & Private | 500,000 UER | 2 years
1.8.2 | Within the framework of "Kutaisi solid waste integrated management program" set up a waste transfer station in Tsageri municipality, which will serve Lentekhi and Tsageri municipalities. | Lentekhi | GOG | 250,000 EUR | 2 years
1.8.3 | Municipalities to gradually introduce and operate waste collection systems for separate collection of municipal waste educational activity of the population for the transition to full-fledged waste separation. | Both | GOG/LSG/NGO | TBD | 4 - 5 years
Results | Increasing the efficiency of waste collection.

## 2. Tourism Products
SI 2.1 | Promote unlimited “off-piste” skiing opportunities around Tetnuldi ski-area | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
2.1.1 | Design and maping off-piste ski runs around ski-resort | Mestia, Lentekhi | MTA | no cost | 1 year
2.1.2 | Install avalanche safety, alarm and rescue system | Mestia, Lentekhi | MTA | TBD | 3 years
2.1.3 | Include off-piste ski opportunities & maps in destination marketing efforts | Mestia, Lentekhi | GMGA / DMO | TBD | Varies
Results | Increase of ski-lift sales by 25% per year.
SI 2.2 | Develop new ski trails around existing resorts (Tetnuldi and Hatsvali) and beyond |  | Responsible Party | Estimated Budget | Estimate Timeline
2.2.1 | Produce and distribute ski-touring trail maps | Mestia, Lentekhi | DMO | 50,000 EUR | 1 year
2.2.2 | Design and build guidelines to define number, location and investment for the overnight huts and shelters | Mestia, Lentekhi | DMO/donors | 15,000 EUR | 1 year
2.2.3 | Desvelop and establish functional emergency rescue system | Mestia, Lentekhi | MTA / MoIA-emergency services | 150,000 EUR | 3 years
Results | Increase safety operations, overnights and visitor number by 20%
SI 2.3 | Host international winter festivals and sporting events |  | Responsible Party | Estimated Budget | Estimate Timeline
2.3.1 | Contract multi-year hosting agreements with Freeride and Highlander. | Mestia | MTA/DMO/Donors | 200,000 EUR | 1-3 years
2.3.2 | Search and submit hosting proposals for other international events | Mestia | DMO/MTA | No Cost | Ongoing
2.3.3 | Develop calendar and host annual sport fests and events | Mestia, Lentekhi | DMO | No cost | 1 year
Results | Attract high spender adventurers - 30% during the event week and a week after. Svaneti will become known in the international market as a competitive destination for hosting mountain events.
SI 2.4 | Develop a “heritage trail” that retraces historical events and folk festivals |  | Responsible Party | Estimated Budget | Estimate Timeline
2.4.1 | Develop the Caucasus Mountain Explorers trail (research, planning, producing, marketing). | Mestia, Lentekhi | DMO, local NGS, Mayor | 50,000 EUR | 1 year
2.4.2 | Ideate other heritage trail themes to develop and promote. | Mestia, Lentekhi | DMO | No Cost | ongoing
Results | Increased tourism, preservation of cultural traditions, economic growth, enhanced visitor experiences, and a competitive edge in the tourism industry.
SI 2.5 | Revitalize historic villages and heritage sites for living history experiences |  | Responsible Party | Estimated Budget | Estimate Timeline
2.5.1 | Organize and promote thematic performances, interpretation and storytelling experiences. | Mestia, Lentekhi | DMO | 50,000 EUR | 1-3 years
Results | Increased tourism, preservation of cultural traditions, economic growth, enhanced visitor experiences, and a competitive edge in the tourism industry.
SI 2.6 | Connect historic communities & valleys with new equestrian, mountain biking and hiking trails |  | Responsible Party | Estimated Budget | Estimate Timeline
2.6.1 | Conduct maintenance to reactivate historical "village to village" trails. | Mestia, Lentekhi | DMO / Trekking guides | 100,000 EUR | 3 years
Results | Extend tourism operation zones by introducing network of the historic tarils - more visitors to the remote villages.
SI 2.7 | New regional trails connecting Svaneti, Samegrelo, Racha |  | Responsible Party | Estimated Budget | Estimate Timeline
2.7.1 | Connect Upper and Lower Svaneti with 3 to 5 the most scenic trails, mark trails. | Mestia, Lentekhi | DMO / donors | 50,000 EUR | 1 year
2.7.2 | Invest to build huts along the trails - 3 huts Svaneti range/1 hut Tetnuldi/1 hut Ushba. | Mestia, Lentekhi | DMO/MTA/investors | 200,000 EUR | 5 years
Results | Improved connectivity and accessibility due to the establishment of new regional trails; Increase attractiveness of the region by providing comfortable accommodation options.
SI 2.8 | Secure partners to promote concept of “guides-trails-huts-rescue” |  | Responsible Party | Estimated Budget | Estimate Timeline
2.8.1 | Create an affordable scheme to establish regional mountain emergency rescue response. | Mestia, Lentekhi | DMO / 112 / GMGA | TBD | 3-5 years
Results | Rescue system network, communication channels, partnership agreements to secure collective responsibility will be created.
SI 2.9 | Hospitality concept based on “Hosts and Guests” relation accompanied by the improved standards of accommodation, mountain huts, quality of food and entertainment. |  | Responsible Party | Estimated Budget | Estimate Timeline
2.9.1 | Enhance gastornomic experiences and hospitality standards | Mestia, Lentekhi | Tetnuldi school/DMO | 50,000 EUR | 3 years
2.9.2 | Develop a concept of "Mountain Host" | Mestia, Lentekhi | ATS/GMGA / DMO | 25,000 EUR | 1 year
Results | Gastornomic experiences based on the concept - research-training-delivery is created and locally promoted.

## 3. Workforce education
SI 3.1 | Open an Adventure Tourism School branch in Mestia - West Point | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
3.1.1 | Manage grant funding from USAID/industry led skills program, contributor GESP, RDA | Mestia | GMGA/ATS | Funds secured | 2 years
3.1.2 | Complete design and construct building "West Point" | Mestia | GMGA/ATS | Funds secured | 2 years
3.1.3 | Create the Adventure Skills Pathway: ATS West Point's Professional Education Framework | Mestia | GMGA/ATS | Funds secured | 2 years
3.1.4 | Replicate adventure tourism programs in West Georgia | Mestia, Lentekhi | GMGA/ATS West Point/Skills Agency | 1 million EUR | 4 years
Results | Certified adventure guides meeting international standards and making the destination competitive in the adventure tourism market. Successful career-building in adventure tourism for youth from all over Svaneti - 25% p/an.
SI 3.2 | Future Guides Summer Schools and Adventure Tourism Leader Program | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
3.2.1 | Develop a formal program “Adventure Tourism Leader” to Middle and High School pupils. | Mestia, Lentekhi | GMGA/ATS/Skils GMGA/ATS/Skils Agency, Lentekhi & Mestia Mayors Offices, College Tetnuldi | 350,000 EUR | 5 years
Results | Approximately 250 pupils per year trained in winter/summer in mountain sports and basics of guiding. In total up to 1000 middle and high school pupils trained over 5 years
SI 3.3 | International accreditation of qualified trainers in adventure tourism education | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
3.3.1 | Mountain Guide Program accredited by IFMGA (Internationa FederatMountain Guide Program accredited by IFMGA (Internationa Federation of Mountain Guides Associaions) | Mestia | GMGA/ATS West Point/Ministry of Education | 50,000 EUR | 2 years
3.3.2 | Trekking Guide Program accredited by UMILA (International Union of Mountain Leaders) | Mestia | GMGA/ATS West Point/Skills Agency | 30,000 EUR | 2 years
Results | Up to 15 Mountain Guide Course Students graduate ATS and receive IFMGA accreditation, up to 25 TrekkingUp to 15 Mountain Guide Course Students graduate ATS and receive IFMGA accreditation, up to 25 Trekking Guide Course Graduate ATS and receive UIMLA accreditation.
SI 3.4 | Establish a Multi-Source Financing Mechanism for Adventure Guide Training | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
3.4.1 | Develop public-private cooperation mechanisms to generate funds from public, private and donor resources and enure stability of financing youth eduction from grassroots training to graduation of TVET courses | Mestia, Lentekhi | GMGA/ATS, Skills Agency, Ministry of Educqtion, DMO, Donors, Industry | No cost | 2 years
Results | Financing mechanisms of adventure tourism workforce training diversified and stabilized, industry involvement ensured
SI 3.5 | Promote Mountain Guiding Professions through Guide Offices and Enhanced Services | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
3.5.1 | Open an Adventure Guide's portal to select and book certified adventure guides | Mesta, Lentekhi | GMGA | Funds secured | Ongoing
Results | Promotion of certified guides. Increasing attractiveness and trust to the adventure tourism in Georgia.
SI 3.6 | Enhance Safety and Risk Management in Mountain Operations | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
3.6.1 | Develop a training course focusing on Safety and Risk Management | Mestia, Lentekhi | GMGA/ATS & DMO | 30,000 EUR | 1-5 years
3.6.2 | Initiate a safety awareness-raising campaign targeting key stakeholders | Mestia, Lentekhi | GMGA/DMO | 15,000 EUR | 1-5 years
3.6.3 | Establish an Adventure Tourism Forum | Mestia | GMGA/ATS West Point/DMO/Mountain Trails Agency, Resorts Development Agency, GNTA | 125,000 EUR | 5 years
Results | Overall safety level of the adventure tourism indutry increased, image of Svaneti as safe adventure tourism destination established, Mestia's position as a center of adventure torism strengthened
SI 3.7 | Support Skills Development for Local Hospitality and Transport Businesses | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
3.7.1 | Assess of the skills gap among local hospitality providers | Mestia, Lentekhi | DMO/College Tetnuldi | TBD | 1 year
3.7.2 | Tailor training programs to the needs of the hospitality providers | Mestia, Lentekhi | College Tetnuldi/Skills Agency | 60,000 EUR | 2 years
3.7.3 | Offer language and interpretation courses for overland tour drivers | Mestia, Lentekhi | College Tetnuldi/Skills Agency | 30,000 EUR | 2 years
3.7.4 | Develop authenticity-supporting vocational training program - Mountain Host and train young men and women from remote villages of Svaneti | Mestia, Lentekhi | GMGA/ATS West Point/College Tetnuldi/DMO, Skills Agency | 60,000 EUR | 3 years
3.7.5 | Institutionalize and formalize existing spontaneous knowledge in the field of cultural heritage via developing new TVET program - Regional Cultural Guide | Mestia | College Tetnuldi/DMO, Skills Agency | 60,000 EUR | 4 years
Results | Up to 300 hospitality provideres, overland operators/drivers, Mountain Hosts and Regional Cultural Guides trained, overall quality of service increased
SI 3.8 | Enhancing Destination and Trails Management | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
3.8.1 | Design mechanisms to ensure a proper maintanance of the destination places and trails | Mestia, Lentekhi | DMO/Guides office | TBD | 1-5 years
Results | Long-term sustainable development and economic growth.
Note on B35: ====== ID#AAAA0rlppxQ Sylecia Johnston (2023-07-11 20:52:30) @chris.seek@solimarinternational.com - can this be an action under an existing initiative? _Assigned to Chris Seek_

## 4. Global Marketing
SI 4.1 | Create an Effective 1-year Marketing Plan | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.1.1 | Conduct a comprehensive evaluation of previous marketing activities | Mestia, Lentekhi | DMO | no cost | Autumn-Winter 2023
4.1.2 | To optimise investment organize annual meetings with tourism professionals | Mestia, Lentekhi | DMO | 5000 EUR | End of the season
4.1.3 | Review and benchmark destination marketing plans from other DMOs | Mestia, Lentekhi | DMO | no costs | Autumn-Winter 2023
4.1.4 | Create partnership with other DMOs, especially with Kutaisi DMO | Mestia, Lentekhi | DMO | no costs | Ongoing
4.1.5 | Draft marketing plan and share it with the public | Mestia, Lentekhi | DMO | 5000 EUR | End of the year
Results | Collaboration and joint initiatives amongst tourism and marketing stakeholders enhancing Svaneti's tourism marketing efforts. Targeting specific markets with right messages and achieving bigger results.
SI 4.2 | Develop and Maintain the Svaneti website | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.2.1 | Develop a comprehensive website with a user-friendly interface | Mestia, Lentekhi | DMO | 5,000 EUR | 1 year
4.2.2 | Provide detailed information on local businesses, accommodations, attractions, and events. | Mestia, Lentekhi | DMO | No Cost | ongoing
4.2.3 | Maintain the website with regular updates and fresh content (events calendar) | Mestia, Lentekhi | DMO | TBD | Ongoing
Results | Improved accessibility for tourists, enabling them to access essential resources and stay updated on local services and community events. Visitors have access to a wealth of information, making it easier for them to plan their trip, explore local offerings, and support local businesses. The website remains current and relevant, providing accurate and up-to-date information to residents, visitors, and potential investors. Visitors plan their trips based on the calendar.
SI 4.3 | Enhance the Online Presence of Svaneti | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.3.1 | Collaborate with online travel marketplaces and OTAs (Online Travel Agency) | Mestia, Lentekhi | DMO | Varies | Ongoing
4.3.2 | Utilize review networks like Tripadvisor to build credibility | Mestia, Lentekhi | DMO | No Cost | Ongoing
4.3.3 | Engage with a diverse audience on social media platforms through targeted campaigns | Mestia, Lentekhi | DMO | Varies | Ongoing
4.3.4 | Regularly upload high-quality videos and optimize for search visibility - create dedicated channel on Youtube and Tiktok | Mestia, Lentekhi | DMO | Varies | Ongoing
Results | Increased global reach and visibility among adventure-seeking travelers, leading to a higher number of bookings and visitors to Svaneti. Enhanced reputation and trustworthiness among potential travelers, increasing the likelihood of choosing Svaneti based on positive reviews and feedback. Increased brand presence, engagement, and community-building, leading to a larger following and potential travelers becoming advocates for Svaneti. Improved visibility in search results and increased viewership, attracting potential travelers and providing them with immersive experiences of Svaneti.
SI 4.4 | Create Svaneti Visitor Guide and Map | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.4.1 | Develop a visually appealing and comprehensive visitor guide. | Mestia, Lentekhi | DMO | 5000 | Winter-Spring 2024
4.4.2 | Design an accurate and user-friendly map of Svaneti | Mestia, Lentekhi | DMO | 5000 | Winter-Spring 2024
4.4.3 | Distribute the visitor guide and map at strategic locations | Mestia, Lentekhi | DMO | no cost | Ongoing
4.4.4 | Provide a digital version of the visitor guide, regularly update, and incorporate captivating visuals. | Mestia, Lentekhi | DMO | no cost | Ongoing
Results | Wide range of visitors have access to valuable information-highlights, landmarks, attractions, hiking trails, points of interest. Wide availability and accessibility of the visitor guide and map at airports, train stations, hotels.
SI 4.5 | Implement a Storytelling Marketing Campaign | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.5.1 | Craft compelling narratives that highlight the region's unique charm and cultural heritage | Mestia, Lentekhi | DMO | TBD | Winter-Spring 2024
4.5.2 | Incorporate different stories such as the first European adventurers and mountaineers to create attractive experiences and tourism offers | Mestia, Lentekhi | DMO | 10,000 EUR | Spring-Autumn 2024
4.5.3 | Collaborate with local storytellers, artists, and content creators | Mestia, Lentekhi | DMO | TBD | Spring-Autumn 2024
Results | Engage with audience emotionally, fostering a deeper connection with Svaneti and creating a memorable impression.
SI 4.6 | Engage Content Creators and Influencers | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.6.1 | Identify content creators and influencers aligned with Svaneti's brand values and target audience | Mestia, Lentekhi | DMO | No Cost | Ongoing
4.6.2 | Collaborate with content creators and influencers through sponsored trips | Mestia, Lentekhi | DMO | Varies | Ongoing
4.6.3 | Encourage content creators and influencers to produce stunning photography and videography | Mestia, Lentekhi | DMO | Varies | Ongoing
Results | Establish partnerships with individuals who can effectively communicate the essence of Svaneti to their followers, increasing the reach and appeal of the region. Enable these individuals to experience Svaneti firsthand, creating authentic and engaging content that showcases the region's unique offerings and drives interest among their followers. Showcase the natural beauty, cultural heritage, and adventure opportunities of Svaneti through visually captivating images, attracting the attention of potential visitors and inspiring travel to the region.
SI 4.7 | Collaborate with Tour Operators and Travel Agents | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.7.1 | Forge strategic partnerships with established tour operators and travel agents | Mestia, Lentekhi | DMO | Varies | Ongoing
4.7.2 | Develop and curate adventure travel itineraries with tour operators | Mestia, Lentekhi | DMO | Varies | Ongoing
4.7.3 | Organize study tours and invite DMOs from Alpine countries to share experiences | Mestia, Lentekhi | DMO | TBD | Ongoing
Results | Establish collaborative relationships that leverage their expertise to develop and promote adventure packages showcasing Svaneti's unique features. Craft comprehensive travel packages. Exchange knowledge, expertise, and best practices with industry professionals, expanding Svaneti's network and promoting the region as a premier adventure travel destination.
SI 4.8 | Participate in Adventure Travel Trade Shows and Exhibitions | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.8.1 | Engage with publications and media outlets in different European countries | Mestia, Lentekhi | DMO | Varies | Ongoing
4.8.2 | Position Svaneti as a modern skiing and adventure destination with rich cultural heritage in Germany and Northern Europe | Mestia, Lentekhi | DMO | Varies | Ongoing
4.8.3 | Participate in exhibitions such as ITB Berlin or World Travel Market | Mestia, Lentekhi | DMO | Varies | Ongoing
Results | Generate interest among European travelers by collaborating with platforms such as the Geographical Society, BBC, and Travel Channel, creating awareness of Svaneti as an exciting adventure travel destination. Capture the interest of European travelers by showcasing Svaneti's diverse offerings, combining thrilling adventure opportunities with ancient cultural experiences, drawing upon historical archives and explorers' accounts. Connect with European travel agents, influencers, media representatives, representatives of other countries.
SI 4.9 | Launch Targeted Campaigns: Mountaineering, Agritourism, Food Tourism, Extended Vacations, and Exploration | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.9.1 | Launch agritourism campaigns showcasing Svaneti's rural charm and agricultural traditions. | Mestia, Lentekhi | DMO | Starting from 1000 EUR | Ongoing
4.9.2 | Promote food tourism campaigns highlighting Svaneti's gastronomic offerings | Mestia, Lentekhi | DMO | Starting from 1000 EUR | Ongoing
4.9.3 | Position Svaneti as an ideal destination for extended vacations | Mestia, Lentekhi | DMO | Starting from 1000 EUR | Ongoing
4.9.4 | Emphasize Svaneti's unspoiled nature and off-the-beaten-path experiences | Mestia, Lentekhi | DMO | Starting from 1000 EUR | Ongoing
Results | Attract travelers seeking authentic and immersive experiences with local culture and cuisine, offering farm stays, interactive encounters, and farm-to-table dining options. Entice European travelers with unique culinary adventures by featuring local delicacies, traditional recipes, and culinary experiences. Collaborations with local restaurants, food festivals, and showcasing local producers enhance the appeal. Attract European travelers who seek in-depth exploration and meaningful connections by promoting longer stays and diverse activities like hiking, skiing, cultural tours, and village experiences. Attract European travelers who seek in-depth exploration and meaningful connections by promoting longer stays and diverse activities like hiking, skiing, cultural tours, and village experiences.
SI 4.10 | Implement Brand Guidelines | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
4.10.1 | Ensure consistent use of the brand and visuals across all communication channels | Mestia, Lentekhi | DMO | No Cost | Ongoing
4.10.2 | Collaborate with local businesses to align their services and experiences with the Svaneti DMO brand | Mestia, Lentekhi | DMO | No Cost | Ongoing
Results | Maintain brand consistency and coherence in all communication materials, ensuring a cohesive and recognizable representation of Svaneti's brand. Enhance the overall brand image by partnering with local providers who share brand values

## 5. Destination Management
SI 5.1 | Enhance the professional capacities of the DMO Staff | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
5.1.1 | Enroll in professional development learning programs for DMO staff | Mestia,Lentekhi | DMO/GNTA | 5.000 EUR | Autumn-Winter 2023
5.1.2 | Recruit an international DMO professional volunteer to provide mentoring | Mestia,Lentekhi | DMO/GNTA | 15.000 EUR | Autumn-Winter 2023
5.1.3 | Attend international conferences organized for DMO professionals | Mestia,Lentekhi | DMO/GNTA | 5.000 EUR | Winter-Spring 2024
Results | International quality and standardization of alpine destination management
SI 5.2 | Collect Visitor & Service Provider Data in GIS Format for Analysis | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
5.5.1 | Desk research: gather, sort and analyze available tourism data and statistics of Svaneti Region | Mestia,Lentekhi | DMO/GNTA/Geostat | TBD | Autumn-Winter 2023
5.5.2 | Outsource a technology / research vendor through a RFP & TOR project management process for implementing a GIS system and gathering new Svaneti specific data | Mestia,Lentekhi | DMO | 10.000 EUR | Autumn-Winter 2023
5.5.3 | Develop a centralized server-based GIS system that facilitates the storage, management, and analysis of geographic data related to tourism | Mestia,Lentekhi | Selected Vendor | TBD | Ongoing
5.5.4 | Define Components of the GIS System administrative module, Statistics Module, Map Basement, Public User Interface | Mestia,Lentekhi | Selected Vendor | TBD | Ongoing
5.5.5 | Data Collection and Maintenance and train DMO staff to execute direct functions. DMO staff can regularly add new information and make necessary changes. | Mestia,Lentekhi | DMO | TBD | Ongoing
5.5.6 | Cost Optimization: Opt for open-source technologies to minimize costs. Utilize PostgreSQL with the PostGIS module as a reliable database for storing spatial data, and employ QGIS for data input and manipulation. | Mestia,Lentekhi | DMO/Selected Vendor | TBD | Ongoing
Results | Improved understanding of the tourism landscape, informed decision-making, comprehensive data collection, centralized data management, enhanced data analysis and reporting, improved visitor experience, and cost optimization through the use of open-source technologies
SI 5.3 | Increase operational efficiency of DMO Svaneti | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
5.3.1 | Develop a 4-year action plan | Mestia,Lentekhi | DMO | No cost | Autumn-Winter 2023
5.3.2 | Define Quarterly or Biannual Goals | Mestia,Lentekhi | DMO | No cost | Winter-Spring 2024
5.3.3 | Recruit Motivated and Professional Personnel | Mestia,Lentekhi | DMO | TBD | Winter-Spring 2024
5.3.4 | Presence Beyond the Municipal Center - representative network at the destinations | Mestia,Lentekhi | DMO | TBD | Spring-Autumn 2024
5.3.5 | Foster Partnerships and Utilize Tourism Products | Mestia,Lentekhi | DMO | No cost | Summer-Autumn 2024
Results | Annual or multi-year action plans are adopted, a roadmap action plan for activities are adopted, tasks are monitored and executed effectively. Professional and motivated personelle recruited and employed. Enhancement of tourism development not only in the center but also in remote regions of Svaneti. Remote area problems are also identified and solutions applied. The DMO will maximize the utilization of local resources and promote sustainable tourism practices.
SI 5.4 | Destination Svaneti - define its positioning at national and international level | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
5.4.1 | Execute brand guidelines and design clear brandbook using results of the branding assignments. | Mestia,Lentekhi | DMO/Consultant | 10,000 EUR | 1 year
Results | Consistent and cohesive brand identity of Svaneti.
SI 5.5 | Destination management network and partnership between public and private actors | Municipality | Responsible Party | Estimated Budget | Estimate Timeline
5.5.1 | Conduct quartarly meeting with the founders and partners | Mestia,Lentekhi | DMO/Industry leaders | 5000 EUR | Annual
5.5.2 | Initiate and facilitate functioning of the "svaneti tourism forum" - network of public-private partners | Mestia,Lentekhi | DMO/Industry leaders | 5000 EUR | Annual
Results | Improved communication, collaboration, and alignment among stakeholders.

## Annex C - Milestones (hidden)
Reference No.: GRETA-SC-....../2023 Terms of Reference of Preparation of a “Svaneti Tourism Development Strategy and Action Plan (Destination Management Plan) “ in cooperation with the Destination Management Organization (DMO) of Svaneti, the public authorities of Mestia and Lentekhi municipalities and other local stakeholders in Upper and Lower Svaneti Project/Programme Title: GRETA ¦ Green Economy: Sustainable Mountain Tourism and Organic Agriculture Country: Georgia ADA Contract Number: ADA ID No. 6542-00/2018 EU Identification Number: EU ID No. ENI/2018/401-348 Implementer: Austrian Development Agency (ADA) Budget Line: 6.1.2.1 Destination management plan Name of Partner/Donors Organizations: European Union Delegation, Swedish Embassy, Austrian Development Cooperation
Deliverables and outputs |  | Deadline
Deliverable # 1: Inception Report
Output # 1.1 | Action plan and timeline: Inception report (no more than 5 pages) briefly summarizing the approach to be adopted and detailed action plan and timeline that will guide the rest of the assignment. This report will be submitted to the Project Manager in electronic format no more than 14 working days after the contract signing. | 14 working days after the contract signing. By January 2023
First payment |  | Beginning of February 2023
Deliverable # 2: Desk research and study assessment report for Mestia and Lentekhi (winter and summer seasons)
Output # 2.1 | Desk research materials and proofs, as follows: 1 - GRETA documents and information including, but not limited to: - Branding Strategy for the destination Svaneti - Baseline Study - GRETA third annual report - Svaneti DMO Professional Capacity Needs Assessment ARC Report - Report of the Tbilisi Workshop of all Georgian DMOs dedicated to collecting DMO feedback for the draft tourism law 2 - Literature/ Document/ Data at regional level, including, but not limited to: - Upper Svaneti Local Development Strategy (2022-2027) - Mestia Municipality 2022-2027 Local Development strategy - Strategy on Development of the Mountainous Regions of Georgia for 2019-2023 3 - Literature/ Document/ Data at national level, including, but not limited to - COVID-19 Tourism Recovery Strategy for Georgia: Regenerating Tourism’ New Potential 2021–2030 - Georgian Tourism Development Strategy 2025 - Agriculture and Rural Development Strategy of Georgia 2021-2027 - Georgia Regional Development Program (2018-2021) - Georgia Mountain Settlements Development Strategy (2019-2023) and Action Plan (2019-2020); - Development Strategy for the Samegrelo-Zemo Svaneti Region (2014-2021) - Law of Georgia on the Development of Mountainous Regions (2015) 4 - Literature/ Document/ Data at international level, including, but not limited to: - Political-Economic Transition in Georgia and its implications for tourism in Svaneti, Georgia; FHGR (previously named HTW), https://www.researchgate.net/publication/279448620_Political-Economic_Transition_in_Georgia_and_its_implications_for_tourism_in_Svaneti | From February to April 2023
Output #2.2 | Two (2) field trips: one (1) for Mestia and one (1) for Lentekhi with the aim to:
· Obtain relevant information about the current situation in tourism (winter and summer seasons)
· Identify current lacks/obstacles/gaps regarding the relevant general infrastructure (winter and summer seasons)
· Obtain relevant information about the existing tourism offer (winter and summer seasons)
· Identify the most important current winter and summer seasons tourism attractions/products/points of interest/services/events
· Identify potential future areas/zones for tourism product development for the winter and summer seasons
· Better understand the sentiments of the local population towards tourism development (winter and summer seasons)
The field trip should not focus on the main touristic centres only but also include villages and more remote rural areas and should foresee to include stakeholder interviews (regional DMO of Svaneti, GNTA, tour guides, tour operators, local entrepreneurs/public representatives, Mountain Resorts of Georgia, etc.).
Output # 2.3 | One draft assessment report for both regions consisting of Mestia and Lentekhi, including winter and summer attractions/products/points of interest/services/events with the aim to:
· Analysis and evaluation of relevant framework conditions (geographic location, population, accessibility, climate, history, etc.)(winter and summer seasons)
· Analysis and evaluation of relevant general infrastructure/issues (transport infrastructure, water supply, wastewater and other waste management, electricity supply, urban/rural zoning, emergency and medical services, local food production) in Upper and Lower Svaneti (winter and summer seasons)
· Analysis and evaluation of key tourism indicators (demand and supply) of Upper and Lower Svaneti (winter and summer seasons)
· Analysis and evaluation of current winter and summer seasons tourism attractions/ products/points of interest/services/events in Upper and Lower Svaneti
· Analysis and evaluation of current winter and summer seasons trends in mountain destinations
· Analysis and evaluation of current tourism marketing )(winter and summer seasons)
· Winter and summer seasons analysis and evaluation of competitors and best practice examples
· SWOT - analysis and evaluation winter and summer seasons for Upper and Lower Svaneti
· PESTEL - identifies the political, economic, social, technological, environmental and legal factors (winter and summer seasons)
· COMPETITOR ANALYSIS - identifies competitor destinations’ brands, product offerings and visitor markets/profiles, share of visitors, visitor nights and visitor expenditure (winter and summer seasons).
· Identification of potential future areas/zones for tourism product development for the winter and summer seasons in Upper and Lower Svaneti
· Identification of potential future tourism attractions/ products/points of interest/services for the winter and summer seasons in Upper and Lower Svaneti ( especially “soft” winter activities and experiences which do not depend on ski lifts).
Output # 2.4 | Two (2) stakeholder workshops (one in Mestia municipality and one in Lentekhi municipality) with the aim to:
present and discuss the findings from field trips and to agree on the key development directions. One of the main aims is to assist and update the regional DMO of Svaneti regarding existing and potential future winter and summer tourism highlights and possibilities to further development of tourism in agreed strategic directions, including a priority/urgency system.
Workshop reports (Indicating feedback from the target groups and consensus reached)
Output # 2.5 | One final approved assessment report
Prepare and submit the final version of the assessment report
Formulate a practical, user-friendly report and submit an electronic copy in English and Georgian languages
Second payment |  | Beginning of May 2023
Deliverable # 3: Draft of the Strategy and Action Plan for Mestia and Lentekhi (winter and summer seasons)
Output # 3.1 | Prepare a first draft of the Strategy and Action Plan for Upper and Lower Svaneti (winter and summer seasons) | From May to July 2023
This draft should be based on the findings of Deliverable # 2 and should define concrete actions/projects/recommendations for the defined key development strategies for Upper and Lower Svaneti including, but not limited to:
· Definition of main source markets/target groups (winter and summer seasons)
· Definition of typical visitor personas for Upper and Lower Svaneti and matching their interests with the current offer (winter and summer seasons)
· Definition of a strong but realistic vision for tourism development in and of key development goals for Upper and Lower Svaneti (winter and summer seasons)
· Definition of the strategic positioning of Upper and Lower Svaneti (winter and summer seasons)
· Definition of key development directions for Upper and Lower Svaneti in the fields of:
o Tourism infrastructure (winter and summer seasons)
o Events (winter and summer seasons)
o Tourism attractions (winter and summer seasons)
o Tourism marketing (winter and summer seasons)
o Cooperation (winter and summer seasons)
o General infrastructure (e.g., village renewal, waste management, water supply, electricity supply etc.)(winter and summer seasons)
o Framework conditions (e.g., urban/rural planning, building restrictions, emergency management)
o Inclusion (e.g., young/old/minorities/ people with disabilities)(winter and summer seasons)
· Know-how transfer (winter and summer seasons)
· Quality improvement (winter and summer seasons)
· Description of the actions/projects
· Definition of the necessary steps
· Definition of the responsible party for implementation
· Investment/Budget estimation
· Determination of potential sources for financing
· Presentation of best practice examples
The draft must clearly differentiate between public and private competences in the development of Svaneti as a tourism destination and should clearly focus on actions/projects for the regional DMO of Svaneti taking the level of urgency (prioritization) and the available financing possibilities into consideration.
Output # 3.2 | Two (2) stakeholder workshops (one in Mestia municipality and one in Lentekhi municipality) with the aim to:
present and discuss the findings from Output # 3.1 The DMO’s input must be given highest attention and agreement must be reached on all core topics and directions, since the DMO will be the owner and driver of the Tourism Development Strategy for Svaneti.
Workshop reports (Indicating feedback from the target groups and consensus reached)
Output # 3.3 | One final approved draft of the Strategy and Action Plan for Mestia and Lentekhi (winter and summer seasons)
Prepare and submit the final draft of the Strategy and Action Plan for Mestia and Lentekhi (winter and summer seasons)
Formulate a practical, user-friendly final draft of the Strategy and Action Plan for Mestia and Lentekhi (winter and summer seasons) and submit an electronic copy in English and Georgian languages
Third payment |  | Beginning of August 2023
Deliverable #4: Final Strategy and Action Plan for Mestia and Lentekhi
Output # 4.1 | Recommendations received from GNTA and local and national related Authorities | In August 2023
In close cooperation with relevant Georgian Government Authorities/Entities elaborate recommendations on how the Georgian Government (central and local) can support a sustainable tourism development in Svaneti
Due to the current administrative system in Georgia, a successful regional tourism development will also need the support of the national, as well as local government. Therefore, concrete recommendations for national, as well as local government support of the destination Svaneti should be defined with close cooperation with the relevant government stakeholders.
Output # 4.2 | One final approved Strategy and Action Plan for Mestia and Lentekhi (winter and summer seasons)
Prepare and submit the final Strategy and Action Plan for Mestia and Lentekhi (winter and summer seasons)
Formulate a practical, user-friendly final Strategy and Action Plan for Mestia and Lentekhi (winter and summer seasons) and submit an electronic copy in English and Georgian languages
Output # 4.3 | Brochure containing a brief outline of the Strategy and Action Plan for both Upper and Lower Svaneti prepared and printed in English and Georgian languages.
Output # 4.4 | Executive summary for the public dissemination prepared and printed in English and Georgian languages.
Output # 4.5 | One presentation event conducted in Mestia to introduce the final Svaneti Tourism Development Strategy and Action Plan to the public, invited guests and government stakeholders
Output # 4.6 | Final short highlight report submitted to GRETA. This highlight report should not be longer than ten (10) pages and cover only the most important facts and details as an overview with reference to the full report (in English and Georgian languages).
Fourth payment |  | Beginning of September 2023
TOTAL